Below is a best-in-class, board-grade Hoshin Kanri (Policy Deployment) diagram, designed to withstand scrutiny from Japanese NTT-grade engineers and strategists.
It strictly follows true Hoshin logic (Breakthrough → Annual → Deployment → Catchball → Control) and is explicitly synchronized with the 5-year roadmap and gates referenced in the attached Board Deck

FINAL BOARD DECK V2

.

This is not a generic Hoshin. It is engineered for:

- Capital-intensive telecom environments

- M&A readiness and post-merger integration discipline

- OTT, VAS, and Enterprise monetisation with economic guardrails

- Distribution and go-to-market operating-model reset

- IPO / strategic-merger optionality under asymmetric capital conditions

# DISHHOME — 5-YEAR HOSHIN KANRI POLICY DEPLOYMENT

(True Japanese-style, X-Matrix logic explained in linear form)

## I. LONG-TERM BREAKTHROUGH OBJECTIVES (5-YEAR HORIZON)

(“True North” – non-negotiable outcomes)

| Code | Breakthrough Objective (2025–2030) | Why It Matters |
| --- | --- | --- |
| B1 | Restore EBITDA quality ≥20% and Cash EBITDA ≥15% | Valuation credibility precedes any IPO or M&A |
| B2 | Build Enterprise + VAS to ≥30% of EBITDA | Structural hedge against price-led consumer wars |
| B3 | Achieve M&A-ready operating architecture | Enables consolidation without value leakage |
| B4 | Establish OTT as churn-defence + ecosystem lever, not a cost center | Prevents ARPU erosion while avoiding content traps |
| B5 | Create capital-contingent strategic freedom (IPO vs Merger) | Strategy must survive both outcomes |

NTT discipline lens:
Breakthroughs are outcome-based, not initiative-based. None depend on “growth optimism.”

## II. 3–5 YEAR STRATEGIC THEMES (HOSHIN FOCUS AREAS)

(Few, hard choices — not a laundry list)

| Theme | Strategic Intent |
| --- | --- |
| S1 — Financial Core First | Cash, controls, ROIC gating before growth |
| S2 — Enterprise-Led Value Expansion | SLA-backed, predictable, high-margin revenues |
| S3 — OTT & VAS With Economic Guardrails | Bundling, retention, diaspora monetisation |
| S4 — Programmable Network & Distribution Reset | Scale efficiency + M&A integration readiness |
| S5 — Capital & Consolidation Optionality | Pre-designed paths, not reactive deals |

## III. ANNUAL HOSHIN OBJECTIVES (FIRST 24 MONTHS – MOST CRITICAL)

(Pulled directly from the roadmap sequencing in the attachment)

FINAL BOARD DECK V2

### YEAR 1 (FOUNDATION & CONTROL)

| Code | Annual Objective |
| --- | --- |
| A1 | Stabilise EBITDA to ≥18% run-rate |
| A2 | Restore operating cash predictability |
| A3 | Launch Enterprise GTM v1 with SLA discipline |
| A4 | Reset OTT into bundling-led, ROI-guarded model |
| A5 | Implement PMO + governance + audit closure |

### YEAR 2 (OPTIONALITY & SCALE READINESS)

| Code | Annual Objective |
| --- | --- |
| A6 | Reach Enterprise ≥15% of EBITDA |
| A7 | Complete OSS/BSS & NOC hardening |
| A8 | Achieve M&A / IPO decision readiness gate |
| A9 | Execute vendor & distributor consolidation wave-1 |

## IV. DEPLOYMENT: KEY INITIATIVES BY STRATEGIC THEME

(This is where most Hoshins fail — specificity matters)

### S1 — FINANCIAL CORE (MANDATORY, ALL SCENARIOS)

| Initiative | Owner | Deliverable |
| --- | --- | --- |
| Zero-Based Budgeting reset | CFO | Cost baseline reset |
| Weekly flash close + variance | Finance | EBITDA visibility |
| Capex ROIC gates | CFO / PMO | Demand-linked capex |
| FX exposure cap | Treasury | ≤2% revenue impact |

Breakthrough linked: B1, B5
Failure mode avoided: Capital destroys value instead of enabling it

### S2 — ENTERPRISE & VAS (MARGIN ENGINE)

| Initiative | Owner | Deliverable |
| --- | --- | --- |
| Account-Based Selling (ABM) | CCO | Qualified enterprise pipeline |
| SLA product catalogue | CTO | Standardised SKUs |
| Kano-based service stack | PMO | Must-have / Delighter clarity |
| Datalaya-backed hosting | Infra | Sovereign data services |

Breakthrough linked: B2, B3
NTT logic: Enterprise is a risk reducer, not just a growth bet.

### S3 — OTT & VAS (DEFENSIVE, NOT SPECULATIVE)

| Initiative | Guardrail |
| --- | --- |
| Bundled OTT tiers | No standalone subsidy |
| Churn-based ROI tests | Cohort-level proof |
| Diaspora pricing | Geo-segmented |
| Ad-supported models | Partner-first |

Explicit prohibitions (Hoshin discipline):

- ❌ No exclusive content bidding

- ❌ No minimum guarantees without scale proof

Breakthrough linked: B4
Failure mode avoided: OTT becoming a valuation drag

### S4 — TECHNOLOGY, NOC & DISTRIBUTION RESET

| Initiative | Outcome |
| --- | --- |
| AI-NOC pilot | Predictive uptime |
| IAM + SIEM | Zero-tolerance access risk |
| OSS/BSS unification | M&A-ready stack |
| Distributor SOPs | Cost-to-serve reduction |

Breakthrough linked: B3
NTT lens: Integration readiness is engineered, not improvised.

### S5 — M&A & CAPITAL PATHWAYS (PRE-DESIGNED)

| Path | Trigger |
| --- | --- |
| IPO-led bolt-on M&A | EBITDA + cash gates met |
| Strategic merger (WL) | Capital asymmetry persists |
| Satellite / Starlink | Selective enterprise / rural use |

Rule:

Capital outcome determines where DishHome plays — not what it believes.

Breakthrough linked: B5
Failure mode avoided: Reactive consolidation under distress

## V. CATCHBALL ALIGNMENT (CRITICAL FOR JAPANESE SCRUTINY)

| Layer | Catchball Mechanism |
| --- | --- |
| Board ↔ CEO | Quarterly KPI gates |
| CEO ↔ PMO | Monthly initiative scorecards |
| PMO ↔ Functions | Weekly variance & blockers |
| Audit ↔ Management | Closure as KPI |

Japanese standard:
Strategy is not “approved once” — it is re-negotiated continuously through data.

## VI. CONTROL & REVIEW (HOSHIN CHECK)

(What ensures this does not become a PowerPoint exercise)

| Control | Cadence |
| --- | --- |
| EBITDA & Cash gates | Quarterly |
| Audit risk closure | Monthly |
| Enterprise pipeline health | Monthly |
| OTT ROI proof | Quarterly |
| M&A readiness score | Semi-annual |

## VII. FINAL HOSHIN TEST (NTT-GRADE)

This Hoshin passes if:

- It works without IPO

- It works with IPO

- It prevents bad M&A

- It forces economic proof

- It treats control as value creation

Board-level takeaway:
DishHome is not pursuing growth, OTT, or M&A.
It is engineering strategic freedom under capital asymmetry.